## Sheet1
Dự án | Hệ thống website bán giày
Công nghệ | php + laravel + MySQL
Thành viên | Phạm Anh Tuân - 3119560078 Lê Duy Khanh - 3119560030 Hồ Văn Diện - 3119560004 Nguyễn Minh Thắng - 3119560065
Github | https://github.com/patuan0810/PTPMMNM
|  |  |  | September | [26 empty] | October | [30 empty] | November
|  |  |  | Week 1 | [7 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
Task name | Owner | Start date | End date | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Design System
Requirements | Tuân & Khanh & Diện | 2022-09-04 | 2022-09-10 | bar: Week 1 4 to Week 1 10
Draw UML diagram | Thắng | 2022-09-11 | 2022-09-17 | bar: Week 1 11 to Week 2 17
Design Use case | Thắng | 2022-09-18 | 2022-09-22 | bar: Week 2 18 to Week 3 22
Design DB | Diện | 2022-09-23 | 2022-09-28 | bar: Week 3 23 to Week 4 28
WEB FOR ADMINISTRATION Implement / Coding for Authentication, Authorization, Admin Module
Build master layout(Header, Body, Footer, Sidebar/Navbar) | Thắng | 2022-09-29 | 2022-10-04 | bar: Week 4 29 to Week 5 4
UI for Manager dashboard | Khanh
UI for Sign-in, Sign-out
UI for Manage users
UI for Manage category
UI for Manage product
UI for Manager blog | Thắng
UI for Manager customers
UI for Manage statistical
UI for Manager bills
Integrate API to Front-end | Khanh
API for dashboard
API for Manager product
API for Manager bill | Thắng
API for Manager customer
API for Manager statistical
WEB FOR USERS
Build master layout(Header, Body, Footer, Sidebar/Navbar) | Diện | 2022-09-29 | 2022-10-04 | bar: Week 4 29 to Week 5 4
UI for Sign-up, Sign-in, Forgot password
UI for homepage
UI for product | Tuân
UI for product - detail
UI for products favorite
Ui for contact
UI for cart | Diện
UI for checkout
UI for blog
UI for search | Tuân
UI for order
UI for manage profile
Integrate API to Front-end
API for homepage, product
API for sign-in, sign-up | Diện
API for checkout